| Borusan EnBW Enerji Istanbul, Turkey |  |  |  |
| --- | --- | --- | --- |
| Saros Hybrid Solar Power Plant |  |  |
| ENVIRONMENTAL SOCIAL ACTION PLAN |  |  |
| Rev. | 0 |  |  |
| Description | Draft |  |  |
| Prepared by | F. Turan, M. Gash, E. Dogru |  |  |
| Controlled by | E. Dogru, T. Cinar |  |  |
| Approved by |  |  |  |
| Date | July 2023 |  |  |

# ENVIRONMENTAL AND SOCIAL ACTION PLAN

An Environmental and Social Action Plan (ESAP) has been developed for Saros Hybrid Solar Power Plant project to address gaps and issues identified during the Environmental and Social Impact Assessment (ESIA). The ESAP is produced for better management of mitigation and performance improvement measures and actions. The mitigation measures are actions designed to ensure that the Project will be in compliance with relevant national legislation, as well as IFC PSs and applicable IFC EHS Guidelines.

The ESAP is structured to include:

- key actions that should be undertaken by the Project to be compliant;

- environmental and social risks (liabilities or benefits) related with the action;

- the applicable legislative requirements;

- the resources to be used, any investment needs, and responsible to implement the action;

- timetable presents an implementation deadline referring to the development of the Project activities, where priority level for closing out the ESAP items are indicated with yellow (low priority), orange (medium priority), or red (high priority);

- target and evaluation criteria indicating the action is implemented successfully;

- the risk levels of the ESAP items are classified as Low (L), Low to Medium (L to M), Medium (M), Medium to High (M to H) and High (H) to identify the potential risk associated with the failure in compliance with the Project ESAP; and

- the score of the performance indicator.

The following shows the score indicator to be used for the ESAP during construction and operational monitoring of the Project.

| EC | Exceeding Compliance: The project has gone beyond the expectations of IFC PSs requirements. Lenders should be able to use projects rated EC as a role model for positive Environmental and Social effects. |
| --- | --- |
| FC | Fully Compliant: The project is fully in compliance with IFC PSs requirements, and EU and local environmental, health and safety policies and guidelines. |
| PC | Partial Compliance: The project is not in full compliance with IFC PS requirements, but has systems, processes or mitigation measure in place which are working towards addressing the deficiencies. |
| MN | Material Non-compliance: The project is not in material compliance with IFC PS requirements, and the systems, processes and mitigation measures in place are not working towards addressing the deficiencies. |

| No. | Action | Environmental & Social Risks (Liability/Benefits) | Requirement (Legislative, IFC PSs, Good Industry Practice) | Resources, Investment Needs, Responsibility | Timetable | Target and Evaluation Criteria for Successful Implementation | Risk Level (L,M,H) | Score |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PS1 | Assessment and Management of Environmental and Social Impacts and Issues |  |  |  |  |  |  |  |  |
| 1.1 | Ensure the following permits are obtained prior to the construction: - System Usage Agreement - Approved Zoning Plan - Preliminary and Final Design Approval | Compliance with national legislation | PS1- Environmental Authorisation National legislation | BORUSAN | Prior to and during the construction | Permits obtained in accordance with the legislation. | H | PC |
|  | Ensure the following permits are obtained during construction in case of need: - Water supply permit for tankers transferring dust suppression water - Waste disposal / collection permit - Wastewater Collection / disposal permit - Agreements with licensed suppliers (e.g. material for backfilling, road stabilization, concrete etc.) | Compliance with national legislation | PS1- Environmental Authorisation National legislation | BORUSAN | Prior to and during the construction | Permits obtained in accordance with the legislation. | H | PC |
|  | Ensure the following permits are obtained prior to the operation: - Provisional Acceptance - Workplace Opening and Operating Permit - Waste Management Plan Approval - Water supply permit for panel cleaning | Compliance with national legislation | PS1- Environmental Authorisation National legislation | BORUSAN | Prior to Operation | Permits obtained in accordance with the legislation. | H | PC |
| 1.2 | Implement Project Construction Environmental and Social Management Plan (ESMP). Implement Project Operation ESMP incorporating the IFC and national requirements. | Sound management of E&S performance of the Project Ensuring and monitoring Contractors’ and sub-contractors’ implementation of the E&S management plans Compliance with the local legislation and IFC PSs. | PS1- Environmental and Social Management Systems Good Industry Practice | BORUSAN Contractors Involvement of external consultants, if needed | During construction | Construction ESMP is in place and implemented | H | PC |
|  |  |  |  |  | One month prior to operation | Operation ESMP is developed and implemented. It is recommended to update Saros WF O-ESMP to cover Solar PV related risks, mitigations, training and audit requirements. | H | PC |
| 1.3 | Implement Project specific E&S management plans for the construction and operation phases of the Project. Where applicable, corporate level | Sound management of E&S performance of the Project Ensuring and monitoring Contractors’ and sub-contractors’ implementation of the E&S management plans Compliance with the local legislation and IFC PSs. | PS1- Environmental and Social Management Systems Good Industry Practice | BORUSAN Contractors Assignment of responsibilities Involvement of external consultants, if needed | Prior to Financial Closure Plans to be implemented during construction and operation | E&S management plans are in place (project specific management plans are developed or corporate level plans are tailored where applicable) and implemented during construction: - Pollution Prevention and Control Plan - Dust and Air Emission Control Plan - Noise Management Plan - Camp Site Management Plan - Traffic Management Plan - Security Management Plan - Training Plan - Waste Management Plan - Community Health and Safety Management Plan - Emergency Preparedness and Response Plan - Occupational Health and Safety Management Plan - Labour Management Plan - Chance Find Procedure - Biodiversity Management Plan - Stakeholder Engagement Plan - Land Acquisition Plan | M | PC |
|  |  |  |  |  | Operation phase plans to be developed at least two months prior to operation | The following E&S management plans are in place and implemented (project specific management plans are developed by updating existing Saros WF operation phase management plans where applicable or corporate level plans are tailored where applicable) for the project for the operation phase and implemented: - Pollution Prevention and Control Plan - Noise Management Plan - Security Management Plan - Training Plan - Waste Management Plan - Community Health and Safety Management Plan - Emergency Preparedness and Response Plan - Occupational Health and Safety Management Plan - Biodiversity Management Plan - Stakeholder Engagement Plan | M | PC |
| 1.4 | Ensure the Project organizational chart defining roles and responsibilities (including ESMS positions) with specific names of individuals is in place and up-to-date for both construction and operation. | Ensure on-going compliance with national legislative requirements and IFC PSs Ensure effective and continuous E&S performance through implementation of the ESMS | PS1- Environmental and Social Management Systems Good Industry Practice | BORUSAN Contractors Assignment of responsibilities | Prior to construction | HSE Organisational structure for construction provided Construction EHS Specialist and CLO to be appointed. | L to M | PC |
|  |  |  |  | BORUSAN O&M Contractor Assignment of responsibilities | Prior to operation | HSE Organisation structure for operation to be developed Operation Phase EHS Responsible and CLO to be appointed | L to M | PC |
| 1.5 | Ensure periodic internal monitoring reports are made available to Lender’s Advisor. | Ensure and demonstrate on-going compliance with national legislation and lender requirements. Identify opportunities for improvements in the provision, application and efficacy of E&S plans and procedures within the ESMS, to optimise the E&S performance of the project. | PS1 - Project monitoring and reporting Good Industry Practice | BORUSAN Contractors Assignment of responsibilities | Quarterly during the construction | Periodic construction E&S Monitoring Reports developed | M | PC |
|  |  |  |  |  | Annually during the financing period | Periodic operation E&S Monitoring Reports developed | M | PC |
| 1.6 | Undertake periodic monitoring/audits of the Contractors, covering E&S, HR and HS issues. | Ensure effective E&S management during construction. | PS1 -Environmental and Social Management Plan | BORUSAN Assignment of responsibilities | Quarterly during the construction | Periodic monitoring/audits are conducted. Records are kept and corrective actions are followed up. | M to H | PC |
| 1.7 | Ensure selected EPC Contractor and subcontractors have the appropriate organisational capacity, commitment and competency to manage E&S risks. Ensure that all contracts (including those of the subcontractors) include relevant national, Lender and Project E&S requirement. | To ensure E&S and labour standards are implemented on the ground. | PS1 -Organisational capacity and commitment Good Industry Practice | BORUSAN Assignment of responsibilities | Prior to contractor appointment | Supplier selection criteria is in place. Project E&S requirements to be included in contractor contractual documents, and include relevant EHS KPI for contractors’ performance. | M to H | PC |
| 1.8 | Implement SEP in line with PS requirements for the Project, and update prior to operation. Maintain a register of consultation undertaken, and report to Lenders. Appoint a CLO to implement and manage the SEP. Update and revise the SEP, if required, during life of the Project. | Positive communication with the surrounding communities, efficient stakeholder engagement and hence the possible protection of the assets. | PS1 - Information Disclosure and Stakeholder Engagement | BORUSAN External resources, if required | Prior to construction | CLO to be appointed Consultation register maintained SEP updated periodically and in case of need | M | PC |
|  |  |  |  |  | Prior to operation and ongoing during project lifecycle | SEP updated periodically and in case of need Consultation register maintained | M | PC |
| 1.9 | Implement and maintain grievance mechanism and grievance log for external and internal stakeholders. Disclose the community grievance mechanism to the affected communities and other key stakeholders. Report to Lenders on all grievances received and their resolution. | Manage community expectations and ensure potential issues with community are identified and managed. | PS1 - Grievance Mechanism | BORUSAN External resources Assignment of responsibilities | Prior to construction | External Grievance mechanism made available to local communities via brochures/flyers Internal Grievance mechanism made available to workers Grievance log (external/internal) established | H | PC |
|  |  |  |  |  | On-going during the Project Lifetime | Grievance mechanism and log implemented and maintained. | M to H | PC |
| 1.10 | Non-technical summary of the Project ESIA to be published on the Project website and distributed to the local communities and key stakeholders. | Minimise the risks of low Project acceptance. | PS1 - Information Disclosure and Stakeholder Engagement Good Industry Practice | BORUSAN Assignment of responsibilities | Prior to Financial Closure | NTS of the Project ESIA published on the Project website and distributed to the local communities | H | PC |
| PS2 | Labour and Working Conditions |  |  |  |  |  |  |  |  |
| 2.1 | Ensure implementation of Labour Management Plan (LMP) | Allocated responsibility for project HR management | PS2 - Management of worker relationships Good Industry Practice | BORUSAN Assignment of responsibilities | During construction | LMP is implemented | M to H | PC |
| 2.2 | Ensure all workers are informed and have access to the corporate HR policy, Local Commitment Policy, Code of Conduct for workers and security. Include the requirement to impellent the abovementioned policies and code of conducts in the contract with the Contractors. | Ensure labour management practice is clearly defined so all parties understand their rights and responsibilities, and ethical practices are upheld. Minimise the risk of non-compliance with IFC PS2 in managing the workforce. | PS2 - Non-discrimination and equal opportunity PS2 - Management of worker relationships Good Industry Practice National legislation | BORUSAN External resources, if needed Contractors | Prior to the commencement of the Contractors’ Contracts | Provisions to implement the Project HR Policy included in the Contractors’ Contracts. | M | PC |
|  |  |  |  |  | On-going during construction and operation | Implementation of HR Policy Make HR Policy available to the Project Staff | M | PC |
| 2.3 | Ensure that individual labour contracts are provided to all workers prior to the commence of the employment contract in line with national Labour Law. Update contracts when material changes occur. | Ensure labour management practice is clearly defined so all parties understand their rights and responsibilities, and ethical practices are upheld. Minimise the risk of non-compliance with IFC PS2 in managing the workforce. | PS2 - Management of worker relationships Good Industry Practice National legislation | BORUSAN Contractors | On-going during construction and operation | Individual labour contracts signed with each worker prior to the commence of the employment contract. | H | PC |
| 2.4 | Ensure that all Contractors develop specific risk based OHS procedures, and implements OHS tool box talks in-line with the approved project OHS management system. Health and Safety Performance systems, procedures, monitoring, audits to be in place. | Minimise H&S risks to workers. | PS2 / PS4 – Occupational Health & Safety Legal requirements Good Industry Practice | BORUSAN Contractors Assignment of responsibilities | Prior to commencement of activities with certain OHS risks | Specific risk based OHS procedures are in place | H | PC |
|  |  |  |  | BORUSAN O&M Contractor Assignment of responsibilities | Within one week after the commencement of employment contract | Trainings on OHS Plan implementation provided to all direct and contracted personnel. Refreshing trainings are provided periodic during the construction and operation. | M to H | PC |
| 2.5 | Implement Project specific HSE Training Plan and Programme to ensure appropriate and timely project specific training is provided to direct and contracted Project personnel. | Ensure workers receive appropriate HSE training to reduce risks of accidents and incidents | PS2 – Occupational Health & Safety Good Industry Practice | BORUSAN Contractors Assignment of responsibilities | During the construction | HSE training plan and program is implemented Training records are maintained on site | M to H | PC |
| 2.6 | Implement the formal grievance mechanism for direct and contracted workers in line with the Project SEP and disseminate information about its uses to the workforce. Cover worker grievance mechanism as part of project worker induction programme. | Enable project to address worker concerns and promote good workforce relationships. | PS2 – Grievance Mechanism Good Industry Practice | BORUSAN Contractors Assignment of responsibilities | During the construction | Worker grievance mechanism in place and disseminated amongst workers. HR maintains internal grievance records and log. Report on all grievances and their resolution. | M to H | PC |
| 2.7 | Ensure appropriate accommodation is provided to the direct and contracted workers. | Minimise the risks associated with personnel displeasure Minimise the health risks associated with inadequate accommodation conditions. Help maintaining good worker-management relationships. | PS2-Worker accommodation Good Industry Practice | BORUSAN Contractors Assignment of responsibilities | During construction Periodic during the construction | Camp Site Management Plan is in place and implemented Periodical compliance verification and audits to be undertaken and records to be kept | M to H | PC |
| PS3 | Resource Efficiency and Pollution Prevention |  |  |  |  |  |  |  |  |
| 3.1 | Ensure the Pollution Prevention and Control Plan is implemented | Compliance with national legislation and PS3 | National Standards PS3 | BORUSAN Contractors External resources Assignment of responsibilities | During the construction | Pollution Prevention and Control Plan is in place and implemented KPIs defined in the Pollution Prevention and Control Plan are met Site inspection logs are kept | M to H | PC |
| 3.2 | Perform dust management and monitoring as per Dust and Air Emission Control Plan in case of grievance from the residents of nearby settlements. | Compliance with national legislation and PS3 Preservation of public health and comfort Responding grievances | National Standards PS3 – Ambient Air Quality IFC EHS Guidelines for Wind Energy | BORUSAN Contractors External resources Assignment of responsibilities | During the construction | Visual checks are performed Dust emissions are controlled through implementation of Dust and Air Emission Control Plan All grievances related to air pollution are processed and managed within appropriate timeframes (i.e. evaluate the complaint and where found necessary/applicable conduct one-off Periodic PM10 measurements and implement necessary corrective actions) | H | PC |
| 3.3 | Perform noise management and monitoring as per Noise Management Plan in case of grievance from the residents of nearby settlements. | Compliance with national legislation and PS3 Preservation of public health and comfort Responding grievances | National Standards PS3 - Noise IFC EHS Guidelines for Wind Energy | BORUSAN Contractors External resources Assignment of responsibilities | During the peak period of construction | Noise emissions are controlled through implementation of Noise Management Plan All grievances related to noise are processes and managed within appropriate timeframes (i.e. evaluate the complaint and where found necessary conduct noise monitoring and implement corrective actions) | H | PC |
|  |  |  |  |  | During operation |  | L to M | PC |
| 3.4 | Ensure that good site housekeeping practices are implemented and necessary mitigation measures are taken by the contractors and sub-contractors as per Pollution Prevention and Control Plan. | Compliance with national legislation and PS3 | National Regulations PS3 – Protection of water bodies | BORUSAN EPC Contractor Assignment of responsibilities | During construction | Site inspection is conducted and corrective actions are implemented and followed up. | L to M | PC |
| 3.5 | Ensure that refuelling of vehicles or equipment is conducted on impermeable ground, and the contractor has procedures for emergency/spill response, and for the storage and handling of hazardous fuels, construction materials and wastes. | Reduce risks of loss and contamination of top soil Regulatory compliance Preservation of nature | National Regulations PS3 – Erosion Protection and Topsoil management | BORUSAN Contractors Assignment of responsibilities | During construction | Pollution Prevention and Control Plan is place. | L to M | PC |
|  | Ensure that Project water demand does not pose any risk on capacity of water resource due to panel cleaning. | Compliance with national legislation and PS3 | National Regulations PS3 – Resource Efficiency and Protection of water bodies | BORUSAN Contractors External Consultants where necessary Assignment of responsibilities | Prior to operation | Conduct assessment studies to ascertain the availability of water once the details of panel cleaning are available. Secure necessary permits for water supply. | M | PC |
| PS4 | Community Health, Safety and Security |  |  |  |  |  |  |  |  |
| 4.1 | Ensure that Community Health Safety and Security Plan is implemented during construction and operation | Effective management of community health and safety Minimise H&S risks to community. Minimisation of conflicts over resources, impacts of influx of workers during construction, and other impacts of the project on the community. Minimise potential community H&S risks. | PS4 – Community Health and Safety Turkish and EU Legislation Good Industry Practice | BORUSAN Contractors External Consultants where necessary Assignment of responsibilities | Prior to construction | Project Community Health, Safety and Security Plan is in place and implemented during construction | H | PC |
|  |  |  |  |  | Prior to operation | Project Community Health, Safety and Security Plan is updated to cover the operation phase | M | PC |
|  |  |  |  |  | Within one week after the commencement of employment contract of security personnel | Trainings on Code of Conduct for security personnel, human rights and use of force are provided to all security personnel and records are kept | M to H | PC |
|  |  |  |  |  | During the construction and operation | All grievances related to Project’s security procedures are processed and resolved as appropriate within the timeframes defined in the Project SEP. | M to H | PC |
|  |  |  |  |  | During the construction and operation | On-going monitoring during construction and operation | M to H | PC |
| 4.2 | Ensure implementation of Emergency Preparedness and Response Plan (EPRP) during the construction, including control measures for workers and community safety (fire, explosions, serious injuries, first aid) in respect of national requirements taking in the account lenders requirements and good industrial practice. Develop a separate EPRP for operation phase of the project. | Prevention of incidents and major industrial accidents Promote worker safety during emergency situations Compliance with national legislation | PS4 – Emergency Preparedness and Response Turkish and EU Legislation OHSAS 18001 | EPC Contractor BORUSAN Assignment of responsibilities Allocate resources | During construction | EPRP in place and implemented during construction phase of the project. Records on emergency drill activities and emergency events are kept | M to H | PC |
|  |  |  |  | O&M Contractor BORUSAN Assignment of responsibilities Allocate resources | Prior to operation | EPRP to be developed/updated to cover operational aspects of the project. Records on emergency drill activities and emergency events are kept | M to H | PC |
| PS5 | Land Acquisition and Involuntary Resettlement |  |  |  |  |  |  |  |  |
| 5.1 | Develop and implement Land Acquisition Plan (LAP) to compensate land owners and land users. The LAP will identify any losses related to the project activities including land and livelihoods regardless of formal title. | Ensure legal ownership of land Minimise risk associated with land ownership claims and future compensation claims Minimise impact on the affected people | National law PS5 – Land Acquisition | BORUSAN External resources Assignment of responsibilities Allocate resources | During construction | Develop and implement LAP and if deemed necessary by LAP develop and implement LRP Consent agreements are signed with landowners | H | PC |
| 5.2 | Implement Stakeholder Engagement Plan (SEP) specifically for the LAP. Ensure the grievances related to land acquisition are processed as per SEP. | Ensure all land owners and land users have project information, understand the compensation process and have access to a grievance mechanism. Ensure compliance with IFC PS5 Ensure the minimization of impact on the affected people | PS5 – Land Acquisition | BORUSAN Assignment of responsibilities Allocate resources | During construction | Grievances are logged, including description of main issues and how they were resolved | H | PC |
| 5.3 | The LAP should also include monitoring/auditing by lenders advisor to ensure land and compensation acquisition process compliance with IFC PS 5; this should also assess whether affected people may suffer despite compensation. | Ensure the minimization of impact on the affected people | PS5 – Land Acquisition | BORUSAN Assignment of responsibilities Allocate resources | Prior to operation | Land acquisition activities are documented and made available for monitoring by Lenders Advisor | M to H | PC |
| PS6 | Biodiversity Conservation and Sustainable Management of Living Natural Resources |  |  |  |  |  |  |  |  |
| 6.1 | Formulate the construction and operational BMP The BMP should: - Ensure all mitigation measures listed in the ESIA are included in the BMP and follow the mitigation hierarchy: avoidance, minimisation, on-site restoration and offsetting/compensation. - Include sufficient actions for no net-loss of natural habitats. - Include actions to avoid further damage to trees, and have a qualified ecologist on site where further trees must be removed. - Include actions to ensure the protection of Common Tortoise during construction and operational monitoring measures - Include actions to use biological control or mechanical control methods of weed control rather than using chemicals if required during operation. - Include actions to use biological control methods for rats instead of chemicals which may harm other fauna - Include a sufficient screening programme for invasive alien species during construction, reinstatement works and operation. The BMP should also include actions for continuous monitoring of the following target biodiversity features to cover pre-construction, construction and operation phases, as per PS6 GN6 Paragraph 89: - Target bird, mammal and herpetofauna species. - Regular bird and vegetation surveys in the construction and operational phases. - Monitoring of vegetation under the transmission lines - to be undertaken by an ecologist during construction - Bird and vegetation surveys at the ETL power line and tower locations During operation, the transmission lines should also be monitored to check collision/electrocution impacts on birds. Should this be considered a significant impact, appropriate adaptive management should be undertaken. | Ensure the project has a minimal impact on ecological receptors. Preservation of habitats, flora and fauna | IFC PS6, PS6 GN6, national legislation for protected sites and species, best practice guidelines for impact assessment. | Project Company Actual work to be undertaken by suitably qualified local biodiversity specialists | BMP to be developed prior to August 2023. Implementation during construction and operation. | BMP is followed and measures are taken to minimise impacts on ecological receptors. Operational monitoring is undertaken to demonstrate no net-loss of species or habitats. | L to M |  |
| PS8 | Cultural Heritage |  |  |  |  |  |  |  |  |
| 8.1 | Implement Change Find Procedure for construction Phase Provide trainings to the workers on what to do in case of chance finding on site | Preservation of cultural heritage items. Manage project delay risks. | PS8 - Chance find procedure Good Industry Practice | EPC Contractor | Implementation throughout the construction phase | Chance find procedure is implemented. Trainings records are kept | L to M | PC |